## Slide 1
ODS Target-State Platform: Decision Plan
Milestone plan to a ratified decision by October 9, covering target platform, deployment pattern, and three-year TCO
Criteria closed
Peer feedback addressed and closed Aug 21; evaluation criteria stand at v2.1
Databricks engaged
Lakebase demonstrated; responding to the evaluation document
Sizing issued
Reference volumetrics annex ready; issued identically to all vendors with the pack
Target | Milestone | Outcome
Aug 21 | Complete | Peer feedback on the evaluation criteria addressed and closed; document at v2.1
Aug 28 | Ratify | Scoring weights ratified and vendor field confirmed
Sep 10 | Engage | Evaluation pack issued to selected vendors; initial demonstrations held and responses documented
Sep 18 | Score | Weighted scoring of responses; field narrowed to two or three platforms for in-depth demonstrations
Oct 2 | Validate | Proof of concept and targeted validation against the performance requirements, in a Global Payments data-platform-relevant architecture
Oct 9 | Decide | Recommendation with deployment pattern and TCO; leadership review and sign-off
Guardrails: criteria-driven weighted scoring · validation before decision, not after · dual-cloud (AWS + Google Cloud) and PCI attestation as gates · TCO assessed at current and 10× volume

## Slide 2
Vendor Field and Platform Name
Five vendors, held deliberately small; every entry clears the dual-cloud and PCI gates or is already engaged
Vendor | Why in the field | What we press hardest
MongoDB Atlas | Document model for multi-key lookups; multi-cloud clusters across AWS and Google Cloud; PCI DSS 4.0; native Iceberg change-stream export; positive POC already completed | Active-active posture: primary-routed writes vs true multi-primary; contractual SLA ceiling (99.995%)
Databricks Lakebase | Already engaged; managed Postgres inside the lakehouse; Unity Catalog native; built-in lakehouse sync removes a pipeline | Scale class (built for 10K+ QPS vs our 100K ops/sec), multi-region active-active, Google Cloud availability
Couchbase Capella | Document model with active-active cross-datacenter replication (XDCR); workload isolation through separated services; PCI DSS 4.0 attested | Latency at our sustained throughput; SLA ceiling; payments references at comparable scale
ScyllaDB Cloud | Sub-millisecond-class latency at high throughput; multi-datacenter active-active; PCI DSS certified; runs on AWS and Google Cloud | Multi-key access-pattern fit and secondary indexes; operating model for a lean platform team
Aerospike | Payments-proven at extreme scale; sub-millisecond reads; active-active XDR with a strong-consistency multi-site option | Managed-service maturity versus self-operated; day-2 operability for a lean platform team
Deliberately excluded: DynamoDB and Cosmos DB (single-cloud; fail the dual-cloud gate) · Redis (in-memory economics against 14–90-day hot windows). Strong products, wrong constraints.
PROPOSED PLATFORM NAME
CREST · Recommended
Current-state Real-time Enterprise Serving Tier
TIDE fills the lake; CREST serves the now.
CURRENT
Current-state data, served in real time
Note: overlaps a major streaming-industry conference name
HALO
High-Availability, Low-latency Operational store
Named for the platform’s defining reliability posture